## Project Timeline
Phase | Task/Milestone | Owner(s) | Start Date | End Date | Status
Phase 1: Foundation | Mini framework with 10 ops | Grishma | 2025-09-03 | 2025-09-15 | Completed
| Core files: graph, tensor, schema, autodiff, ops, CMake | Grishma | 2025-09-03 | 2025-09-15 | Completed
Phase 2: Onboarding | Rishi: Basics learning | Rishikanth | 2025-09-15 | 2025-10-09 | Completed
| Kurra: Codebase dissection | Kurra | 2025-09-15 | 2025-10-09 | Completed
| Nabil: Codebase dissection | Nabil | 2025-09-29 | 2025-10-09 | Completed
Phase 3: Tools & Ops | Debug tools, export_hlo, dummy jit::compile | Grishma | 2025-09-15 | 2025-10-05 | Completed
| Kernel_loader and kernel_api | Grishma | 2025-10-01 | 2025-10-10 | Completed
| Add 30-40 ops | Nabil | 2025-10-01 | 2025-10-31 | Completed
| GPU kernels | Nabil | 2025-10-01 | 2025-10-31 | Completed
| CPU kernels | Kurra | 2025-10-01 | 2025-10-31 | Completed
Phase 4: Memory & Integration | Memory management (checkpointing, inplace, versioning) | Kurra | 2025-10-10 | 2025-10-31 | Completed
| Framework study & tape paper | Rishikanth | 2025-10-10 | 2025-10-31 | Completed
| CUDA graphs (initial) | Grishma | 2025-10-15 | 2025-10-17 | Completed
| Memory safegaurd - NoDiscard Macro | Rishikanth | 2025-10-16 | 2025-10-31 | Completed
| Tensor library integration | Grishma | 2025-10-25 | 2025-11-05 | Completed
| Split ops into ops.cpp and nodeops.cpp | Nabil | 2025-10-25 | 2025-10-31 | Completed
Phase 5: Tracer Development | New members joined: Jenifa, Jona, Surendra | Team | 2025-11-01 | 2025-11-01 | Completed
| FX graph generation & static mode | Kurra (lead) | 2025-11-01 | 2025-11-20 | Completed
| Tracer implementation | Jenifa, Jona, Surendra | 2025-11-01 | 2025-11-20 | Completed
| Pybinding framework | Nabil | 2025-11-08 | 2025-11-10 | Completed
Phase 6: C++ Focus | Meeting: Shift to C++ only (no Python) | Team | 2025-11-11 | 2025-11-11 | Completed
| Nabil leaves team | Nabil | 2025-11-11 | 2025-11-11 | Completed
| Comp graph → TAC lowering | Jona, Rishikanth, Kurra | 2025-11-12 | 2025-11-30 | Completed
| TAC → MLIR lowering | Grishma, Jenifa, Surendra | 2025-11-12 | 2025-11-30 | Completed
Phase 7: Direct MLIR | Decision: Skip TAC, direct to MLIR in SSA | Team | 2025-11-25 | 2025-11-25 | Completed
| Direct MLIR lowering (in-memory SSA) | Grishma, Jenifa, Surendra | 2025-11-26 |  | In Progress
Phase 8: Refactoring & Optimization & Memory+CUDAGrapg | Refactor nodeops (primitives) | Rishikanth, Kurra, Jona | 2025-12-01 |  | In Progress
| Dependency counter algorithm (CPU) | Grishma, Jenifa | 2025-12-01 |  | In Progress
| Memory Arena | Rishikanth | 2025-11-01
| Checkpointing Types(Selective, Adaptive) | Kurra, Surendra | 2025-11-02
Phase 9: GPU Autograd Parallel | Multi-stream backward execution | TBD |  |  | Planned | 1
| GPU gradient checkpointing | TBD |  |  | Planned | 3
Phase 10: Higher-Order AD | Grad-of-grad (second derivatives) | TBD |  |  | Planned | 5
| Hessian computation | TBD |  |  | Planned
| Hessian-vector products | TBD |  |  | Planned
Phase 11: Composite Data Structure Support | Accept Composite Data structures of Tensors | TBD |  |  | Planned | 2
| like list, dictionary, sparse, tuple etc... of tensors | TBD |  |  | Planned
Phase 12: Forward-Mode AD | Forward-mode autodiff engine | TBD |  |  | Planned | 4
| JVP composition with backward | TBD |  |  | Planned
Phase 13: Custom Gradients | Custom VJP/JVP definitions | TBD |  |  | Planned | 7
| Gradient override decorators | TBD |  |  | Planned
| Stop gradient / detach semantics | TBD |  |  | Planned
Phase 14: Advanced Gradients | Implicit differentiation | TBD |  |  | Planned | 8
| Gradient sparsity support | TBD |  |  | Planned
| Lazy gradient evaluation | TBD |  |  | Planned
| Selective backprop | TBD |  |  | Planned
Phase 15: Gradient Optimization | Gradient accumulation strategies | TBD |  |  | Planned
Phase 16: Memory Management and Garbage Collection | Graph Cleanup | TBD |  |  | Planned | 6
| Gradient Explosions | TBD |  |  | Planned
| Memory Leaks | TBD |  |  | Planned
| GPU Memory Pool | TBD |  |  | Planned
| Memory Profiling | TBD |  |  | Planned

## WBS with Gantt Chart
WBS | Task Name | Owner(s) | Start | End | Duration | % Done | Sep W35 | Sep W36 | Sep W37 | Sep W38 | Sep W39 | Oct W40 | Oct W41 | Oct W42 | Oct W43 | Nov W44 | Nov W45 | Nov W46 | Nov W47 | Dec W48 | Dec W49 | Dec W50 | Dec W51 | Dec W52
1 | Core Framework
1.1 | Graph Engine | Grishma | 2025-09-03 | 2025-09-15 | 13d | 80% | █ | █ | █
1.2 | Autodiff (Memory Mgmt) | Kurra | 2025-10-10 | 2025-10-31 | 22d | 70% | [5 empty] | █ | █ | █ | █
1.3 | Autodiff (Checkpointing) | Kurra, Surendra | 2025-12-01 | 2025-12-13 | 13d | 75% | [13 empty] | █ | █
1.4 | Tensor Ops (Initial) | Grishma, Nabil | 2025-09-03 | 2025-11-30 | 89d | 100% | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
1.5 | Nodeops Refactoring | Rishikanth, Kurra, Jona | 2025-12-01 | 2025-12-13 | 13d | 60% | [13 empty] | █ | █
2 | Kernel Infrastructure(Deprecated)
2.1 | CPU Kernels | Kurra | 2025-10-01 | 2025-10-31 | 31d | 100% |  |  |  |  | █ | █ | █ | █ | █
2.2 | GPU Kernels | Nabil | 2025-10-01 | 2025-10-31 | 31d | 100% |  |  |  |  | █ | █ | █ | █ | █
2.3 | Kernel Loader & API | Grishma | 2025-10-01 | 2025-10-10 | 10d | 100% |  |  |  |  | █ | █
3 | Compilation & Execution
3.1 | JIT Compile (Dummy) | Grishma | 2025-09-15 | 2025-10-05 | 21d | 50% |  |  | █ | █ | █
3.2 | JIT Refactoring | Grishma | 2025-12-01 | 2025-12-13 | 13d | 100% | [13 empty] | █ | █
3.3 | CUDA Graphs (Initial) | Grishma | 2025-10-15 | 2025-10-17 | 3d | 100% | [6 empty] | █
3.4 | CUDA Graphs | Rishikanth, Jona | 2025-12-01 | 2025-12-13 | 13d | 50% | [13 empty] | █ | █
3.5 | Graph → TAC | Jona, Rishikanth, Kurra | 2025-11-12 | 2025-11-30 | 19d | 100% | [10 empty] | █ | █ | █
3.6 | TAC → MLIR | Grishma, Jenifa, Surendra | 2025-11-12 | 2025-11-30 | 19d | 100% | [10 empty] | █ | █ | █
3.7 | Direct MLIR (SSA) | Grishma, Jenifa, Surendra | 2025-11-26 | 2025-12-13 | 18d | 30% | [12 empty] | █ | █ | █
3.8 | Dependency Counter | Grishma, Jenifa | 2025-12-01 | 2025-12-13 | 13d | 25% | [13 empty] | █ | █
4 | PyTracer: Static Mode(dropped)
4.1 | FX Graph & Static Mode | Kurra | 2025-11-01 | 2025-11-20 | 20d | 20% | [8 empty] | █ | █ | █ | █
4.2 | Tracer Implementation | Jenifa, Jona, Surendra | 2025-11-01 | 2025-11-20 | 20d | 20% | [8 empty] | █ | █ | █ | █
5 | Integration & Build
5.1 | Tensor Library Integration | Grishma | 2025-10-25 | 2025-11-05 | 12d | 100% | [7 empty] | █ | █ | █
5.2 | Build System (CMake) | All | 2025-09-03 | 2025-12-13 | 102d | 100% | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
6 | Tooling & Utilities
6.1 | Debug Tools | Grishma | 2025-09-15 | 2025-10-05 | 21d | 100% |  |  | █ | █ | █
8 | Future: GPU Autograd
8.1 | Multi-stream Backward | TBD |  |  |  | 0%
8.2 | GPU Gradient Checkpointing | TBD |  |  |  | 0%
9 | Future: Higher-Order AD
9.1 | Grad-of-Grad Engine | TBD |  |  |  | 0%
9.2 | Hessian Computation | TBD |  |  |  | 0%
9.3 | Hessian-Vector Products | TBD |  |  |  | 0%
10 | Future: Forward-Mode AD
10.1 | Forward-Mode Engine | TBD |  |  |  | 0%
10.2 | JVP Composition | TBD |  |  |  | 0%
11 | Future: Custom Gradients
11.1 | Custom VJP/JVP API | TBD |  |  |  | 0%
11.2 | Gradient Overrides | TBD |  |  |  | 0%
11.3 | Stop Gradient Semantics | TBD |  |  |  | 0%
12 | Future: Advanced Gradients
12.1 | Implicit Differentiation | TBD |  |  |  | 0%
12.2 | Gradient Sparsity | TBD |  |  |  | 0%
12.3 | Lazy Gradient Eval | TBD |  |  |  | 0%
12.4 | Selective Backprop | TBD |  |  |  | 0%
13 | Future: Gradient Optimization
13.1 | Gradient Accumulation | TBD |  |  |  | 0%
13.2 | Dead code elimination in backward | TBD |  |  |  | 0%
13.3 | Gradient Accumulation | TBD |  |  |  | 0%
14 | Future: Memory Management And Garbage Collections
14.1 | Gradient Explosions | TBD |  |  |  | 0%
14.2 | Graph Cleanup | TBD |  |  |  | 0%
14.3 | Memory Leaks | TBD |  |  |  | 0%
14.4 | GPU Memory Pool | TBD |  |  |  | 0%
14.5 | Memory Profiling | TBD |  |  |  | 0%

## Team Tasks
Team Task Breakdown - Timeline Visualization
Team | Member | Task | Days | Cumulative Days
Team 1 | kurra | debugging present checkpointing | 4 | 4
Team 1 | kurra | adaptive checkpointing impl | 3 | 7
Team 1 | kurra | chens algo impl | 5 | 12
Team 1 | surendra | read&understand existing checkpointing in general | 4 | 4
Team 1 | surendra | understand checkpointing of framework | 3 | 7
Team 1 | surendra | uniform checkpoint impl | 3 | 10
Team 1 | surendra | forward recompute in checkpointing impl | 2 | 12
Team 2 | jenifa | thread pool impl and basic worker loop | 1.5 | 1.5
Team 2 | jenifa | integrate readyqueue ith worker and shutdown logic | 1.5 | 3
Team 2 | jenifa | merge & integrate to backward() | 1 | 4
Team 2 | jenifa | refactor half the functions adding this functionalit to nodeops. | 2 | 6
Team 2 | jenifa | testing | 2 | 8
Team 2 | jenifa | brainstrom on edge cases | 1 | 9
Team 2 | jenifa | implement the edge cases | 2 | 11
Team 2 | jenifa | learn cuda_Stream | 3 | 14
Team 2 | grishma | implement dependency counter map and initialization | 1.5 | 1.5
Team 2 | grishma | implement counter decrement logic and parent readying | 1.5 | 3
Team 2 | grishma | merge and intigrate backward | 1 | 4
Team 2 | grishma | refactoring nodeops | 2 | 6
Team 2 | grishma | testing | 2 | 8
Team 2 | grishma | brainstrom on edge cases | 1 | 9
Team 2 | grishma | implement the edge cases | 2 | 11
Team 2 | grishma | learn cuda_Stream | 3 | 14
Team 3 | rishi | general disection and outline | 3 | 3
Team 3 | rishi | CUDA mem pool(disection) | 3 | 6
Team 3 | rishi | with stream cudagraph(toy implementation based of our fraamework) | 4 | 10
Team 3 | rishi | testing | 2 | 12
Team 3 | jona | general disection and outline | 3 | 3
Team 3 | jona | graph capture and executor | 3 | 6
Team 3 | jona | w/o cudastrem cudagraph(toy implementation based of our fraamework) | 4 | 10
Team 3 | jona | testing | 2 | 12
Task Checklist
☐ | Team | Member | Task | Days
☐ | Team 1 | kurra | debugging present checkpointing | 4
☐ | Team 1 | kurra | adaptive checkpointing impl | 3
☐ | Team 1 | kurra | chens algo impl | 5
☐ | Team 1 | surendra | read&understand existing checkpointing in general | 4
☐ | Team 1 | surendra | understand checkpointing of framework | 3
☐ | Team 1 | surendra | uniform checkpoint impl | 3
☐ | Team 1 | surendra | forward recompute in checkpointing impl | 2
☐ | Team 2 | jenifa | thread pool impl and basic worker loop | 1.5
☐ | Team 2 | jenifa | integrate readyqueue with worker and shutdown logic | 1.5
☐ | Team 2 | jenifa | merge & integrate to backward() | 1
☐ | Team 2 | jenifa | refactor half the functions adding this functionalit to nodeops. | 2
☐ | Team 2 | jenifa | testing | 2
☐ | Team 2 | jenifa | brainstrom on edge cases | 1
☐ | Team 2 | jenifa | implement the edge cases | 2
☐ | Team 2 | jenifa | learn cuda_Stream | 3
☐ | Team 2 | grishma | implement dependency counter map and initialization | 1.5
☐ | Team 2 | grishma | implement counter decrement logic and parent readying | 1.5
☐ | Team 2 | grishma | merge and intigrate backward | 1
☐ | Team 2 | grishma | refactoring nodeops | 2
☐ | Team 2 | grishma | testing | 2
☐ | Team 2 | grishma | brainstrom on edge cases | 1
☐ | Team 2 | grishma | implement the edge cases | 2
☐ | Team 2 | grishma | learn cuda_Stream | 3
☐ | Team 3 | rishi | general disection and outline | 3
☐ | Team 3 | rishi | CUDA mem pool(disection) | 3
☐ | Team 3 | rishi | with stream cudagraph(toy implementation based of our framework) | 4
☐ | Team 3 | rishi | testing | 2
☐ | Team 3 | jona | general disection and outline | 3
☐ | Team 3 | jona | graph capture and executor | 3
☐ | Team 3 | jona | w/o cudastrem cudagraph(toy implementation based of our framework) | 4
☐ | Team 3 | jona | testing | 2